## Oversikt
Overview | Project | Program | Portfolio | Project | Program | Portfolio | Project | Program | Portfolio | Project | Program | Portfolio | Project | Program | Portfolio | Project | Program | Portfolio | Project | Program | Portfolio
P3M3 ® Maturity Levels
Level 5 - Optimized process
Level 4 - Managed process
Level 3 - Defined process
Level 2 - Repeatable process
Level 1 - Awareness of process
| Organizat. Govern. |  |  | Mgmt. Control |  |  | Benefits Mgmt. |  |  | Risk Mgmt. |  |  | Stakeholder Mgmt. |  |  | Financial Mgmt. |  |  | Resource Mgmt.

## Prosjekt
Project Management
P3M3 ® assessment form |  |  | Ja | Nei | Delvis |  | Ja | Nei
Organizational Governance | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This looks at how the delivery of initiatives is aligned to the strategic direction of the organization. It considers how start-up and closure controls are applied to initiatives and how alignment is maintained during an initiative’s life cycle. This differs from management control, which views how control of initiatives is maintained internally, as this perspective looks at how external factors that impact on initiatives are controlled (where possible, or mitigated if not) and used to maximize the final result. Effective sponsorship should enable this. Organizational governance also looks at how a range of other organizational controls are deployed and standards achieved, including legislative and regulatory frameworks. It also considers the levels of analysis of stakeholder engagement and how their requirements are factored into the design and delivery of outputs and outcomes. | The criterias of level 1 are not fullfilled |  |  | Some informal governance of projects exists but has undefined links to broader organizational controls. Roles are unlikely to be formally defined. |  |  |  | Project management from an organizational perspective is beginning to take shape but with ad hoc controls and no clear strategic control. Roles and responsibilities will be inconsistent, as will reporting lines. |  |  | Centrally defined organizational controls are applied consistently to all projects, with decision-making structures in place and linked to organizational governance. |  |  | There will be clearly aligned project decision-making processes that adopt and integrate with broader organizational governance and which are transparent to those involved. Project management responsibilities are embedded within broader role descriptions. |  |  | The governance arrangements for projects are a core aspect of organizational control, with demonstrable reporting lines to Executive Board level and with clear ownership and control responsibilities embedded within the organization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We launch projects at will, perhaps in response to a particular problem that has arisen. They operate outside day to day governance structures |  |  | Process: We are starting to draw up rules for project approvals and there is sometimes evidence of associated documentation |  |  |  | Process: Our projects are subject to some form of formal approval, although it may be possible to bypass those mechanisms |  |  | Process: We have a common and consistently applied approach to project governance, including an approach to scaling the rigour of project approvals and assurance |  |  | Process: Our project approval process includes criteria to evaluate the value of the project in context of the wider portfolio, not just on its own merit. |  |  | Process: We have a dynamic relationship between the corporate plan and our portfolio of projects, with both being flexed to optimise the achievement of corporate objectives
| Organization: It is unclear how to get decisions made and ratified as there are no decision-making structures defined for our projects other than what is already in place for operational activities. |  |  | Organization: Our projects attempt to define who is authorised to make project decisions but these are made in isolation of other projects |  |  |  | Organization: We generally understand who is authorised to make what type of project decision (e.g. start/stop, approve contracts, assign budgets, hire resources, etc) based on locally defined rules |  |  | Organization: It is clear who is authorised to make what type of project decision and their level of approval based on centrally defined rules. It is clear who is accountable for the success of each project. |  |  | Organization: Our approach to authorisation is continually reviewed based on historical analysis of performance |  |  | Organization: We actively tailor our approach to uthorization to suit the needs of internal and external environments
| Performance: We don't know what projects are running |  |  | Performance: We are beginning to develop a view of what key projects we are running |  |  |  | Performance: We know what key projects are running but do not fully understand how they align to strategic objectives. Projects are rarely stopped |  |  | Performance: We know what projects are running and broadly how they align to strategic objectives. There are examples of projects being stopped or redirected based on past performance or change of strategy |  |  | Performance: We know what projects we are running and how they align to strategic objectives. Forecasts of project performance are used to ensure ongoing re-alignment. |  |  | Performance: Our total investment in projects is optimised to maximise the achievement of strategic objectives for the least time, cost and risk
Management Control | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This covers the internal controls of the initiative and how its direction of travel is maintained throughout its life cycle, with appropriate break points to enable it to be stopped or redirected by a controlling body if necessary. Management control is characterized by clear evidence of leadership and direction, scope, stages, tranches and review processes during the course of the initiative. There will be regular checkpoints and clearly defined decision-making processes. There will be full and clear objectives and descriptions of what the initiative will deliver. Initiatives should have clearly described outputs, a programme may have a blueprint (or target operating model) with defined outcomes, and a portfolio may have an organizational blueprint (or target operating model). Internal structures will be aligned to achieve these characteristics and the focus of control will be on achieving them within the tolerance and boundaries set by the controlling body and based on the broader organizational requirements. Issues will be identified and evaluated, and decisions on how to deal with them will be made using a structured process with appropriate impact assessments. | The criterias of level 1 are not fullfilled |  |  | Project management terminology is used by some members of the organization but not consistently and possibly not understood by all stakeholders. Projects are conducted and managed according to individual preferences. |  |  |  | The concepts of project management will have been grasped by the organization, and there may be local experts, such as experienced project managers, working on key projects. |  |  | There is a centrally defined and documented approach to a project management life cycle and controls, and it is applied in all projects by capable staff who support project teams. |  |  | Project management is seen as a key tool for the delivery mechanism of change. Within the project environment the focus is on improvement of delivery through measurement and analysis of performance. |  |  | Management controls ensure that the project approach delivers the change objectives of the organization. Acceptance of project management as the optimal approach to change delivery is organization-wide. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We have no defined approach to management controls, nor are we aware that we may need one |  |  | Process: There is recognition that we need project-level controls and we are beginning to define them |  |  |  | Process: Our projects have a project lifecycle with defined control points but they are not consistent across the organization |  |  | Process: We have a common approach to project controls (which may include a defined gated lifecycle) that is consistently applied by projects |  |  | Process: We increasingly use performance management, which tells us how effective the project controls are |  |  | Process: We systematically use knowledge management to optimise project controls, with evidence of interventions to address inefficiencies in project delivery
| Organization: Our people are asked to work on projects, but their role/responsibility and effort commitment is undefined |  |  | Organization: We recognise the need for specific project-related roles and responsibilities, and there are occasional examples of a Project Board (or equivalent) being in place. Appointments are still very much of an ad-hoc nature. |  |  |  | Organization: Our projects have roles and responsibilities for project controls defined, but they are not consistent across the organization |  |  | Organization: We have a consistent approach to project roles and responsibilities, including the use of Project Boards (or equivalent) to control direction and delivery |  |  | Organization: Our performance appraisals of people assigned to project roles include the effectiveness of their responsibilities (including responsibilities to provide direction and control to projects) |  |  | Organization: We are optimally structured to integrate projects and operational activities. It is unambiguous who is accountable for what.
| Performance: Our projects are delivered as part of our operational activities and performance is not monitored |  |  | Performance: Few of our projects deliver within original performance targets. Performance targets are rarely set. |  |  |  | Performance: Some of our projects deliver within original performance targets. Performance targets are set (perhaps for time and cost only) |  |  | Performance: Most of our projects deliver within baselined performance targets. Performance targets set for time, cost and benefits |  |  | Performance: All of our projects deliver within baselined performance targets. There is predictability of performance |  |  | Performance: It is rare for our projects to fail, though some are stopped due to external or strategic changes. Diagnostic analysis is undertaken to predict and pre-empt failures
Benefits Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Benefits management is the process that ensures that the desired business change outcomes have been clearly defined are measurable and are ultimately realized through a structured approach and with full organizational ownership. Benefits should be assessed and approved by the organizational areas that will deliver them. Benefit dependencies and other requirements are clearly defined and understanding gained on how the outputs of the initiative will meet those requirements. There should be evidence of suitable classification of benefits and a holistic view of the implications being considered. All benefits should be owned, have realization plans and be actively managed to ensure that they are achieved. There will be a focus on operational transition, coupled with follow-up activities to ensure that benefits are being owned and realized by the organization. There will be evidence of continual improvement being embedded in the way the organization functions. This process will identify opportunities that can be delivered by initiatives and also take ownership of the exploitation of capabilities delivered by programmes and projects. Change management, and the complexities this brings, will also be built into the organization’s approach. | The criterias of level 1 are not fullfilled |  |  | There is some recognition that the concept of benefits can be differentiated from project outputs. |  |  |  | Benefits are recognized as an element within project business cases. There may be some documentation regarding who is responsible for particular benefits and their realization, but this is unlikely to be followed through or consistent. |  |  | There is a centrally managed and consistent framework for defining and tracking the realization of benefits from project outputs. |  |  | Benefits management is embedded within the project management approach and there is a focus on delivery of business performance from project outputs. Project performance metrics are collected and analyzed. |  |  | Benefits management is embedded within the organizational approach to change and is assessed as part of the development of organizational strategy. Business performance metrics are linked to, and underpin, the recognition of benefits realization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognize benefits management activities as part of a project management process. |  |  | Process: There are a few examples of projects defining benefits. Benefits are defined independently of any organizational standards |  |  |  | Process: Our projects document benefits using their own approach and to different levels of detail. The relationship between requirements and benefits may not be clear |  |  | Process: We have a common framework for recording and tracking benefits that is used by all projects |  |  | Process: Our projects use a common range of criteria for benefits and dis-benefits that are linked to our organization's objectives |  |  | Process: We continually monitor for opportunities to improve the effectiveness of our common project benefits management process
| Organization: Responsibilities for ensuring project benefits are realised are not defined |  |  | Organization: There are a few examples of projects defining benefit owners |  |  |  | Organization: In some of our projects, there are commitments from individuals or local groups to take action to ensure that benefits are delivered |  |  | Organization: Responsibilities for the achievement of individual benefits are clearly defined in all of our projects |  |  | Organization: Responsibilities for the achievement of individual benefits are clearly defined in all of our projects. There is an aggregated view of the benefits that our projects will deliver |  |  | Organization: Our organizational structure includes responsibility for pre-emptive interventions into existing projects to redirect them based on forecasting benefits performance
| Performance: We neither define nor measure benefits |  |  | Performance: Few of our projects deliver their expected benefits |  |  |  | Performance: Some of our projects deliver their expected benefits, but evidence may be based on anecdotal observations or indications |  |  | Performance: Most of our projects deliver most of their defined benefits, but full evidence may not always be available |  |  | Performance: Nearly all of our projects deliver most of their expected benefits, and this can be evidenced |  |  | Performance: We can reliably predict when projects will collectively deliver benefits
Risk Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This views the way in which the organization manages threats to, and opportunities presented by, the initiative. Risk management maintains a balance of focus on threats and opportunities, with appropriate management actions to minimize or eliminate the likelihood of any identified threat occurring, or to minimize its impact if it does occur, and maximize opportunities. It will look at a variety of risk types, both internal and external, that affect the initiative and will focus on tracking the triggers that create risks. Responses to risk will be innovative and proactive, using a number of options to minimize threats and maximise opportunities. The review of risk will be embedded within the initiative’s life cycle and have a supporting process and structures to ensure that the appropriate levels of rigour are being applied, with evidence of interventions and changes made to manage risks. | The criterias of level 1 are not fullfilled |  |  | There is minimal evidence of risk management being used to any beneficial effect on projects. There may be evidence of risks being documented but little evidence of active management. |  |  |  | Risk management is recognized and used on projects, but there are inconsistent approaches, which result in different levels of commitment and effectiveness. |  |  | Project risk management is based on a centrally defined process that is cognizant of the organization’s policy for the management of risks and is used consistently. |  |  | Project risk management is working effectively, is embedded, and the value of risk management can be demonstrated. There is evidence of opportunity management and management of risk aggregation. |  |  | Risk management is embedded in the organizational culture and underpins all decision-making within projects. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognize risk management activities as part of a project management process |  |  | Process: There are a few examples of project documentation that reference lists of negative things that may happen |  |  |  | Process: Our projects use their own approaches for the management of risks which may recognise opportunities as well as threats |  |  | Process: We have a common approach to risk management that is used by all projects, and which includes procedures for threats and opportunities |  |  | Process: Our common project risk management process is regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually seeking ways to improve the effectiveness of our common project risk management process
| Organization: Responsibilities for managing risks to our projects are not defined |  |  | Organization: Our projects sometimes identify risk owners |  |  |  | Organization: There are commitments from individuals or local groups to take action to reduce the impact of risks in some of our projects |  |  | Organization: Responsibilities for responding to risks are clearly defined in all of our projects, based on a centrally defined approach |  |  | Organization: We make adjustments to delivery during the project lifecycle, to exploit opportunities and avoid threats |  |  | Organization: Our organizational structure includes responsibility for pre-emptive interventions to re-direct existing projects based on threats and opportunities
| Performance: Our projects are unaware of what things might go wrong |  |  | Performance: Our projects often underperform as a result of risks that could have been anticipated |  |  |  | Performance: Our projects mostly anticipate their risks, but some projects underperform as a result of risks that could have been anticipated |  |  | Performance: Our projects mostly manage their risks, but some underperform as a result of events that were unpredictable (unknown unknowns) |  |  | Performance: Our projects are generally able to handle events that were unpredictable (unknown unknowns) through early warning and risk response mechanisms |  |  | Performance: We are able to optimise our project portfolio through understanding its risk profile
Stakeholder Engagement | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Stakeholders are key to the success of any initiative. Stakeholders at different levels, both within and outside the organization, will need to be analyzed and engaged with effectively in order to achieve objectives in terms of support and engagement. Stakeholder engagement includes communications planning, the effective identification and use of different communications channels, and techniques to enable objectives to be achieved. Stakeholder engagement should be seen as an ongoing process across all initiatives and one that is inherently linked to the initiative’s life cycle and governance controls. | The criterias of level 1 are not fullfilled |  |  | Stakeholder engagement and communication is rarely used by projects as an element of the delivery toolkit. |  |  |  | Projects will be communicated to stakeholders, but this is linked more to the personal initiative of project managers than to a structured approach being deployed by the organization. |  |  | There is a centrally managed and consistent approach to stakeholder engagement and communications used by all projects. |  |  | Sophisticated techniques are used to analyze and engage the project stakeholder environment effectively, and quantitative information is used to underpin the assessment of effectiveness. |  |  | Communications are being optimized from extensive knowledge of the project stakeholder environment, to enable the projects to achieve their objectives. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognize stakeholder management activities as part of a project management process. |  |  | Process: There are a few examples of project documentation that reference lists of stakeholders |  |  |  | Process: Our projects use their own documented approaches for the management of stakeholders and communications |  |  | Process: We have a common approach to stakeholder and communications management that is consistently applied by projects |  |  | Process: Our common project stakeholder management process is regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our common project stakeholder management process
| Organization: No one is responsible for managing our project communications |  |  | Organization: Some projects define responsibilities for project communications |  |  |  | Organization: Our projects have defined responsibilities for stakeholder engagement but they are not consistent across the organization |  |  | Organization: Our projects consistently use central communications function(s) for stakeholder communications according to a centrally defined approach |  |  | Organization: We seek opportunities to consolidate consultation/communication to enable more efficient solicitation of feedback and delivery of project messages |  |  | Organization: We consolidate consultation/communication across multiple projects to optimise stakeholder engagement efficiency and effectiveness
| Performance: Most Stakeholders are unaware of project activities/progress |  |  | Performance: Projects sometimes underperform due to stakeholder resistance |  |  |  | Performance: Stakeholders are engaged, but we are aware of instances of stakeholders receiving multiple or conflicting messages from different sources due to the lack of consistency |  |  | Performance: Stakeholders are consistently engaged by project teams, but there may not be evidence across our projects to gauge the level of stakeholder support |  |  | Performance: Evidence exists that demonstrates stakeholders consistently feel well engaged by our project teams |  |  | Performance: We have a clear view of which projects are engaging which stakeholder groups and use this view to optimise communication
Financial Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Finance is an essential resource that should be a key focus for initiating and controlling initiatives. Financial management ensures that the likely costs of the initiative are captured and evaluated within a formal business case and that costs are categorized and managed over the investment life cycle. There should be evidence of the appropriate involvement of the organization’s financial functions, with approvals being embedded in the broader organizational hierarchy. The business case, or equivalent, should define the value of the initiative to the business and contain a financial appraisal of the possible options. The business case will be at the core of decision-making during the initiative’s life cycle, and may be linked to formal review stages and evaluation of the cost and benefits associated with alternative actions. Financial management will schedule the availability of funds to support the investment decisions. | The criterias of level 1 are not fullfilled |  |  | There is little or no financial control at project level. There is a lack of accountability and monitoring of project expenditure. |  |  |  | Project business cases are produced in various forms and the better and more formal cases will present the rationale on which to obtain organizational commitment to the project. Overall cost of the project is not monitored or fully accounted for. |  |  | There are centrally established standards for the preparation of business cases and processes for their management throughout the project life cycle. Project managers monitor costs and expenditure in accordance with organizational guidelines and procedures, with defined interfaces with other financial functions within the organization. |  |  | The organization is able to prioritize investment opportunities effectively in relation to the availability of funds and other resources. Project budgets are managed effectively and project performance against cost is monitored and compared. |  |  | Project financial controls are fully integrated with those of the organization. Cost estimation techniques used at the project level are continually reviewed in terms of actual versus estimate comparisons to improve estimation throughout the organization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: Our projects are mostly funded from "business as usual" budgets and do not operate under project-based financial processes |  |  | Process: A few of our projects have budgets in place and in some cases are undertaking financial performance reviews |  |  |  | Process: We have local finance management approaches in place for projects including some form of periodic financial review |  |  | Process: 3 We have a common approach to finance management that is used by all projects. There is a gated process to ensure that all projects are subject to reviews of financial viability at pre-defined points of their lifecycle |  |  | Process: Our common finance management process for projects is regularly assessed for past effectiveness and refined when appropriate |  |  | Process: Pre-emptive interventions based on financial reporting forecasts will redirect our existing projects.
| Organization: Our projects do not require any kind of financial approval before they start work |  |  | Organization: Financial approvals for our projects are beginning to emerge |  |  |  | Organization: We have approval bodies in place for major investments, but not all investments go through official approval channels. There is evidence of local accountability in some cases |  |  | Organization: Financial accountability for our projects is managed to corporate standards |  |  | Organization: There is an aggregated view of costs across our projects |  |  | Organization: We have a clear view of forecast costs and funding requirements for all projects within the portfolio(s)
| Performance: Projects do not know their costs |  |  | Performance: Few of our projects deliver within their expected costs |  |  |  | Performance: Some of our projects deliver within their expected costs |  |  | Performance: Most of our projects deliver within their expected costs |  |  | Performance: Nearly all of our projects deliver within their expected costs |  |  | Performance: We can reliably predict the cost profile of our project portfolio to optimize funding
Resource Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Resource management covers management of all types of resources required for delivery. These include human resources, buildings, equipment, supplies, information, tools and supporting teams. A key element of resource management is the process for acquiring resources and how supply chains are utilized to maximize effective use of resources. There will be evidence of capacity planning and prioritization to enable effective resource management. This will also include performance management and exploitation of opportunities for greater utilization. Resource capacity considerations will be extended to the capacity of the operational groups to resource the implications of change. | The criterias of level 1 are not fullfilled |  |  | There is some recognition within the organization of the need to manage resources effectively to enable successful delivery of projects, but little evidence of resource acquisition, planning or management. |  |  |  | Resources are being deployed across the organization and individual projects have an approach to resource acquisition, planning or management. However, there is little evidence of consistency of approach. |  |  | The organization has a centrally defined and adopted set of procedures and management processes for acquiring, planning and managing project resources. |  |  | Resource management for projects is considered at a strategic level within the organization. There is evidence of resource capacity management, through capacity planning, in order to meet project delivery needs. |  |  | Resources are deployed optimally. There is clear evidence of load balancing and the effective use of both internal and external resources across projects. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: Projects rarely identify the resources they require or the means to acquire them |  |  | Process: There are a few examples of projects listing their resource requirements and the means to acquire them in their project documentation |  |  |  | Process: Our projects have their own approaches to resource management. Assumptions about resource availability are made |  |  | Process: We have a common approach to resource management process that is used by all projects |  |  | Process: Our common project resource management process is regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our common project resource management process
| Organization: Acquisition of resources is not managed |  |  | Organization: There are isolated examples of projects managing the acquisition of their own resources |  |  |  | Organization: Our projects define responsibilities for managing the acquisition of resources independently of each other |  |  | Organization: Our projects understand their resource requirements in terms of capacity and capability, and a plan exists to manage them. There is some co-ordination between the projects undertaken by a central function |  |  | Organization: We have a central function that has an aggregated view of resource requirements/utilization across projects and our organizational capacity to deliver them |  |  | Organization: We have a central function which ensures we have the capacity to fulfil demand based on forecast resource requirements/utilisation across our projects
| Performance: Resourcing issues come as a surprise to projects |  |  | Performance: We are aware of instances of resource conflicts due to the lack of resource planning |  |  |  | Performance: Resource performance and utilization tracking is taking place in some of our projects, but it is inconsistently applied |  |  | Performance: Resource performance and utilization tracking is taking place which enables scheduling of key resources between projects |  |  | Performance: We make adjustments to delivery during the project lifecycle, to re-balance resource supply and demand. Projects consistently have sufficient resources to meet their schedule targets. |  |  | Performance: We make pre-emptive interventions based on forecasting performance/utilization to redirect resources in existing projects in order to optimize the number of projects we can deliver

## Program
Programme Management
P3M3 ® assessment form |  |  | Ja |  | Delvis |  | Ja | Nei
Organizational Governance | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This looks at how the delivery of initiatives is aligned to the strategic direction of the organization. It considers how start-up and closure controls are applied to initiatives and how alignment is maintained during an initiative’s life cycle. This differs from management control, which views how control of initiatives is maintained internally, as this perspective looks at how external factors that impact on initiatives are controlled (where possible, or mitigated if not) and used to maximize the final result. Effective sponsorship should enable this. Organizational governance also looks at how a range of other organizational controls are deployed and standards achieved, including legislative and regulatory frameworks. It also considers the levels of analysis of stakeholder engagement and how their requirements are factored into the design and delivery of outputs and outcomes. | The criterias of level 1 are not fullfilled |  |  | Some informal governance of programmes may exist but with undefined links to projects and/or broader organizational controls. Roles are unlikely to be formally defined. |  |  |  | Programme management from an organizational perspective is beginning to take shape but with ad hoc controls and no clear strategic control. Roles and responsibilities will be inconsistent, as will reporting lines. |  |  | Centrally defined organizational controls are applied consistently to all programmes, with decision-making structures in place and linked to organizational governance. |  |  | There will be clearly aligned programme decision-making processes that adopt and integrate with broader organizational governance and which are transparent to those involved. Programme management responsibilities are embedded within broader role descriptions. |  |  | The governance arrangements for programmes are a core aspect of organizational control, with demonstrable reporting lines to Executive Board level and with clear ownership and control responsibilities embedded within the organization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We launch programmes at will, perhaps in response to a particular problem that has arisen. They operate outside or, in conflict with, day to day governance structures |  |  | Process: We are starting to draw up rules for programme approvals, and there is sometimes evidence of associated documentation |  |  |  | Process: Our programmes are subject to some form of formal approval at key points in their lifecycle, although it may be possible to bypass those mechanisms |  |  | Process: We have a common and consistently applied approach to programme governance, including an approach to scaling the rigour of programme/project approvals and assurance |  |  | Process: Our programme/project approval process includes criteria to evaluate the value of the programme (and constituent projects) in context of the wider portfolio, not just on its own merit. |  |  | Process: We have a dynamic relationship between the corporate plan and our portfolio of programmes, with both being flexed to optimise the achievement of corporate objectives
| Organization: It is unclear how to get decisions made and ratified as there are no decision-making structures defined for our programmes other than what is already in place for operational activities. |  |  | Organization: Our Programmes attempt to define who is authorised to make Programme decisions but these are made in isolation of other Programmes |  |  |  | Organization: We generally understand who is authorised to make what type of programme decision (e.g. start/stop, approve contracts, assign budgets, hire resources, etc) based on locally defined rules. |  |  | Organization: It is clear who is authorised to make what type of programme decision and their level of approval based on centrally defined rules; It is clear who is accountable for the success of each Programme |  |  | Organization: Our approach to authorisation is continually reviewed based on historical analysis of performance |  |  | Organization: We actively tailor our approach to authorization to suit the needs of internal and external environments
| Performance: We don't know what programmes are running |  |  | Performance: We are beginning to develop a view of what key programmes we are running |  |  |  | Performance: We have confidence that we know what programmes are running but do not fully understand how they align to strategic objectives; Programmes are rarely stopped |  |  | Performance: We know what programmes are running and how they align to strategic objectives. There are examples of programmes being stopped or redirected based on past performance or change of strategy |  |  | Performance: We know what programmes we are running and how their outcomes align to strategic objectives. Forecasts of programme performance are used to ensure ongoing re-alignment. |  |  | Performance: Our total investment in programmes is optimised to maximise the achievement of strategic objectives for the least time, cost and risk
Management Control | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This covers the internal controls of the initiative and how its direction of travel is maintained throughout its life cycle, with appropriate break points to enable it to be stopped or redirected by a controlling body if necessary. Management control is characterized by clear evidence of leadership and direction, scope, stages, tranches and review processes during the course of the initiative. There will be regular checkpoints and clearly defined decision-making processes. There will be full and clear objectives and descriptions of what the initiative will deliver. Initiatives should have clearly described outputs, a programme may have a blueprint (or target operating model) with defined outcomes, and a portfolio may have an organizational blueprint (or target operating model). Internal structures will be aligned to achieve these characteristics and the focus of control will be on achieving them within the tolerance and boundaries set by the controlling body and based on the broader organizational requirements. Issues will be identified and evaluated, and decisions on how to deal with them will be made using a structured process with appropriate impact assessments. | The criterias of level 1 are not fullfilled |  |  | Programme management terminology is used by some members of the organization but not consistently and possibly not understood by all stakeholders. Programmes are conducted and managed according to individual preferences. |  |  |  | The concepts of programme management will have been grasped by the organization, and there may be local experts, such as experienced programme managers working on key programmes. |  |  | There is a centrally defined and documented approach to a programme management life cycle and controls, and it is applied in all programmes by capable staff who support programme teams. |  |  | Programme management is seen as a key tool for the delivery of strategic change objectives. Within the programme environment the focus is on improvement of delivery through measurement and analysis of performance. |  |  | Management controls ensure that the programme approach delivers the strategic aims and objectives of the organization. Acceptance of programme management as the optimal approach to strategic delivery is organization-wide. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We have no defined approach to controlling programmes and nor are we aware that we may need one |  |  | Process: There is recognition that we need programme-level controls and we are beginning to define them. |  |  |  | Process: Our programmes use lifecycles that include major review points after a major outcome has been achieved, but they are not consistent across the organization; there is recognition for the need to integrate programme and project controls. |  |  | Process: We have a common approach to controls using a defined gated lifecycle that ensures all programmes and their constituent projects are reviewed when transitioning between tranches/stages |  |  | Process: We increasingly use performance management, which tells us how effective the programme controls are |  |  | Process: We systematically use knowledge management to optimise programme controls, with evidence of interventions to address inefficiencies in programme delivery
| Organization: Our people are asked to work on programmes, but their role/responsibility and effort commitment is undefined |  |  | Organization: We recognise the need for specific programme-related roles and responsibilities and there are occassional examples of a Programme Board (or equivalent) being in place. Appointments are still very much of an ad-hoc nature. |  |  |  | Organization: Our programmes have roles and responsibilities for programme controls defined, but they are not consistent across the organization |  |  | Organization: We have a consistent approach to programme roles and responsibilities, including the use of Programme Boards (or equivalent) to control direction and delivery |  |  | Organization: Our performance appraisals of people assigned to programme roles include effectiveness of their responsibilities. They also assess the effectiveness of Programme boards (or equivalent) for their collective responsibilities to provide direction and control. |  |  | Organization: We are optimally structured to integrate programmes and operational activities. It is unambiguous who is accountable for what
| Performance: Our programmes are delivered as part of our operational activities and performance is not monitored |  |  | Performance: Few of our programmes deliver within original performance targets as specified in business cases. Performance targets are rarely set |  |  |  | Performance: Some of our programmes deliver within original performance targets. Performance targets are set in business cases, though they may not be complete (perhaps for time and cost only) |  |  | Performance: Most of our programmes deliver within baselined performance targets. Performance targets set for time, cost and benefits. |  |  | Performance: All of our programmes deliver within specified business case parameters. There is predictability of performance. |  |  | Performance: It is rare for our programmes to fail, though some are stopped due to external or strategic changes. Diagnostic analysis is undertaken to predict and pre-empt failures
Benefits Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Benefits management is the process that ensures that the desired business change outcomes have been clearly defined are measurable and are ultimately realized through a structured approach and with full organizational ownership. Benefits should be assessed and approved by the organizational areas that will deliver them. Benefit dependencies and other requirements are clearly defined and understanding gained on how the outputs of the initiative will meet those requirements. There should be evidence of suitable classification of benefits and a holistic view of the implications being considered. All benefits should be owned, have realization plans and be actively managed to ensure that they are achieved. There will be a focus on operational transition, coupled with follow-up activities to ensure that benefits are being owned and realized by the organization. There will be evidence of continual improvement being embedded in the way the organization functions. This process will identify opportunities that can be delivered by initiatives and also take ownership of the exploitation of capabilities delivered by programmes and projects. Change management, and the complexities this brings, will also be built into the organization’s approach. | The criterias of level 1 are not fullfilled |  |  | There is some recognition that the concept of benefits can be differentiated from programme outcomes. |  |  |  | Benefits are recognized as an element within programme business cases. There may be some documentation regarding who is responsible for particular benefits and their realization, but this is unlikely to be followed through or consistent. |  |  | There is a centrally managed and consistent framework for defining and tracking the realization of benefits arising from programme outcomes. |  |  | Benefits management is embedded within the programme management approach and there is a focus on delivery of business performance from programme outcomes. Programme performance metrics are collected and analyzed. |  |  | Benefits management is embedded within the organizational approach to strategic change and is assessed as part of the development of organizational strategies. Business performance metrics are linked to, and underpin, the recognition of benefits realization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise benefits management activities as part of a programme management process |  |  | Process: There are isolated examples of programmes defining benefits and outcomes; the relationship between outputs, outcomes and benefits is starting to be understood. |  |  |  | Process: Our programmes document benefits using locally defined approaches to different levels of detail which include business change management plans |  |  | Process: Our programmes consistently apply a common framework for delivering capability from project outputs, the resulting outcomes, and the benefits |  |  | Process: Our programes consistently use a defined range of criteria for benefits and dis-benefits that are linked to our organization's objectives |  |  | Process: We continually monitor for opportunities to improve the effectiveness of our common benefits management process
| Organization: Responsibilities for ensuring programme benefits are realised are not defined |  |  | Organization: There are a few examples of programmes defining benefit owners |  |  |  | Organization: In some of our programmes, individuals or local groups are accountable to take action to ensure that benefits are delivered |  |  | Organization: Responsibilities for the achievement of individual benefits are clearly defined in all of our programmes |  |  | Organization: Responsibilities for the achievement of individual benefits are clearly defined in all of our Programmes, their constituent projects and affected operations; There is an aggregated view of the benefits that our programmes will deliver |  |  | Organization: Our organizational structure includes responsibility for pre-emptive interventions into existing programmes to redirect them based on forecasting benefits performance
| Performance: We neither define nor measure benefits |  |  | Performance: Few of our programmes deliver their expected benefits |  |  |  | Performance: Some of our programmes deliver their expected benefits, but evidence may be based on anecdotal observations or indications |  |  | Performance: Most of our programmes deliver most of their defined benefits, but evidence may not always be available |  |  | Performance: All of our programmes deliver most of their expected benefits, and this can be evidenced |  |  | Performance: We can reliably predict when programmes will collectively deliver benefits; some programmes deliver more than their targets
Risk Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This views the way in which the organization manages threats to, and opportunities presented by, the initiative. Risk management maintains a balance of focus on threats and opportunities, with appropriate management actions to minimize or eliminate the likelihood of any identified threat occurring, or to minimize its impact if it does occur, and maximize opportunities. It will look at a variety of risk types, both internal and external, that affect the initiative and will focus on tracking the triggers that create risks. Responses to risk will be innovative and proactive, using a number of options to minimize threats and maximise opportunities. The review of risk will be embedded within the initiative’s life cycle and have a supporting process and structures to ensure that the appropriate levels of rigour are being applied, with evidence of interventions and changes made to manage risks. | The criterias of level 1 are not fullfilled |  |  | There is minimal evidence of risk management being used to any beneficial effect on programmes. There may be evidence of risks being documented but little evidence of active management. |  |  |  | Risk management is recognized and used on programmes, but there are inconsistent approaches which result in different levels of commitment and effectiveness. |  |  | Programme risk management is based on a centrally defined process that is cognizant of the organization’s policy for the management of risks and is used consistently. |  |  | Programme risk management is working effectively, is embedded, and the value of risk management can be demonstrated. There is evidence of opportunity management and management of risk aggregation. |  |  | Risk management is embedded in the culture of the organization and underpins all decision-making within programmes. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise risk management activities as part of a programme management process |  |  | Process: Programmes do not differentiate programme-level risks from project risks |  |  |  | Process: Our programmes use their own approaches for the management of risks. Programme risks are differentiated from project risks |  |  | Process: We have a common approach to risk management that is consistently applied by programmes, which includes procedures for aggregating risks from the programme and its constituent projects |  |  | Process: Our common programme risk management processes are regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our common programme risk management process
| Organization: Responsibilities for managing risks on our programmes are not defined |  |  | Organization: Our programmes sometimes identify risk owners |  |  |  | Organization: There are commitments from individuals or local groups to take action to reduce the impact of risks in some of our programmes |  |  | Organization: Responsibilities for responding to risks are clearly defined in all of our programmes, based on a centrally defined approach |  |  | Organization: We have roles accountable for budgets to respond to risks that are common across our organization. We make adjustments to delivery during the programme lifecycle, to exploit opportunities and avoid threats |  |  | Organization: Our organizational structure includes responsibility for pre-emptive interventions to redirect programmes based on threats and opportunities
| Performance: Our programmes are unaware of what things might go wrong |  |  | Performance: Our programmes often underperform as a result of risks that could have been anticipated |  |  |  | Performance: Our programmes mostly anticipate their risks, but some underperform as a result of risks that could have been anticipated |  |  | Performance: Our programmes mostly manage their risks, but some underperform as a result of unpredictable risks (unknown unknowns) |  |  | Performance: Our programmes are generally able to handle events that were unpredictable (unknown unknowns) through early warning mechanisms and risk response mechanisms |  |  | Performance: We are able to optimise our programme portfolio through understanding its risk profile
Stakeholder Engagement | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Stakeholders are key to the success of any initiative. Stakeholders at different levels, both within and outside the organization, will need to be analyzed and engaged with effectively in order to achieve objectives in terms of support and engagement. Stakeholder engagement includes communications planning, the effective identification and use of different communications channels, and techniques to enable objectives to be achieved. Stakeholder engagement should be seen as an ongoing process across all initiatives and one that is inherently linked to the initiative’s life cycle and governance controls. | The criterias of level 1 are not fullfilled |  |  | Stakeholder engagement and communication is rarely used by programmes as an element of the delivery toolkit. |  |  |  | Some programmes will be communicated to stakeholders, but this is linked more to the personal initiative of programme managers than to a structured approach being deployed by the organization. |  |  | There is a centrally managed and consistent approach to stakeholder engagement and communications used by all programmes. |  |  | Sophisticated techniques are used to analyze and engage the programme stakeholder environment effectively, and quantitative information is used to underpin the assessment of effectiveness. |  |  | Communications are being optimized from extensive knowledge of the stakeholder environment, to enable the programmes to achieve their objectives. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise stakeholder management activities as part of a programme management process |  |  | Process: There are a few examples of programme documentation that reference lists of stakeholders |  |  |  | Process: Our programmes use their own documented approaches for the management of stakeholders and communications |  |  | Process: We have a common approach to stakeholder and communications management that is consistently applied by programmes; Programmes integrate communications across the programme and its constituent projects |  |  | Process: Our common programme stakeholder management processes are regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our common programme stakeholder management process
| Organization: No one is responsible for managing our programme communications |  |  | Organization: Some programmes define responsibilities for communications |  |  |  | Organization: Our programmes have defined responsibilities for stakeholder engagement but they are not consistent across the organization |  |  | Organization: Our programmes consistently use central communications function(s) for stakeholder communications according to a centrally defined approach |  |  | Organization: We seek opportunities to consolidate consultation/communication to enable more efficient solicitation of feedback and delivery of programme messages |  |  | Organization: We consolidate consultation/communication across multiple programmes (and their constituent projects) to optimise stakeholder engagement efficiency and effectiveness
| Performance: Most stakeholders are unaware of programme progress |  |  | Performance: Programmes sometimes underperform due to stakeholder resistance |  |  |  | Performance: Stakeholders are engaged, but we are aware of instances of stakeholders receiving multiple or conflicting messages from different sources due to the lack of consistency |  |  | Performance: Stakeholders are consistently engaged by programmes teams, but there may not be evidence across our programmes to gauge the level of stakeholder support |  |  | Performance: Evidence exists that demonstrates stakeholders consistently feel well engaged by our programme teams |  |  | Performance: We have a clear view of which programmes (and their constituent projects) are engaging which stakeholder groups and use this view to optimise communication
Financial Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Finance is an essential resource that should be a key focus for initiating and controlling initiatives. Financial management ensures that the likely costs of the initiative are captured and evaluated within a formal business case and that costs are categorized and managed over the investment life cycle. There should be evidence of the appropriate involvement of the organization’s financial functions, with approvals being embedded in the broader organizational hierarchy. The business case, or equivalent, should define the value of the initiative to the business and contain a financial appraisal of the possible options. The business case will be at the core of decision-making during the initiative’s life cycle, and may be linked to formal review stages and evaluation of the cost and benefits associated with alternative actions. Financial management will schedule the availability of funds to support the investment decisions. | The criterias of level 1 are not fullfilled |  |  | There is little or no financial control at programme level. There is a lack of accountability and monitoring of programme expenditure. |  |  |  | Programme business cases are produced in various forms and the better and more formal cases will present the rationale on which to obtain organizational commitment to the programme. Overall cost of the programme is not monitored or fully accounted for. |  |  | There are centrally established standards for the preparation of business cases and processes for their management throughout the programme life cycle. Programme managers monitor costs and expenditure in accordance with organizational guidelines and procedures, with defined interfaces with other financial functions within the organization. |  |  | The organization is able to prioritize investment opportunities effectively in relation to the availability of funds and other resources. Programme budgets are managed effectively and programme performance against cost is monitored and compared. |  |  | Programme financial controls are fully integrated with those of the organization. Cost estimation techniques used at the programme level are continually reviewed in terms of actual versus estimate comparisons to improve estimation throughout the organization. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: Our programmes are mostly funded from "business as usual" budgets and do not operate under programme-based financial processes. |  |  | Process: A few of our programmes have budgets in place and in some cases are undertaking financial performance reviews |  |  |  | Process: We have local finance management approaches in place for programmes including some form of periodic financial review |  |  | Process: We have a common approach to finance management that is consistently applied by programmes and their constituent projects. There is a gated process to ensure that all programmes are subject to reviews of financial viability at pre-defined points of their lifecycle |  |  | Process: Our common finance management processes for programmes are regularly assessed for effectiveness and refined when appropriate |  |  | Process: Pre-emptive interventions based on financial reporting forecasts will redirect our existing programmes
| Organization: Our programmes do not require any kind of financial approval before they start work |  |  | Organization: Financial approvals for our programmes are beginning to emerge |  |  |  | Organization: We have approval bodies in place for major investments, but not all investments go through official approval channels. There is evidence of local accountability in some cases |  |  | Organization: Financial accountability for our programmes is managed to corporate standards; programmes are accountable for the finances of their constituent projects |  |  | Organization: There is an aggregated view of the level of costs across our programmes to enable efficiency in securing sufficient funding |  |  | Organization: We have a clear view of forecast cost and funding requirements for all programmes within the portfolio(s)
| Performance: Programmes do not know their costs |  |  | Performance: Few of our programmes deliver within their expected costs |  |  |  | Performance: Some of our programmes deliver within their expected costs |  |  | Performance: Most of our programmes deliver within their expected costs |  |  | Performance: Nearly all of our programmes deliver within their expected costs |  |  | Performance: We can reliably predict the cost profile of our programme portfolio to optimize funding
Resource Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Resource management covers management of all types of resources required for delivery. These include human resources, buildings, equipment, supplies, information, tools and supporting teams. A key element of resource management is the process for acquiring resources and how supply chains are utilized to maximize effective use of resources. There will be evidence of capacity planning and prioritization to enable effective resource management. This will also include performance management and exploitation of opportunities for greater utilization. Resource capacity considerations will be extended to the capacity of the operational groups to resource the implications of change. | The criterias of level 1 are not fullfilled |  |  | There is some recognition within the organization of the need to manage resources effectively to enable successful delivery of programmes, but little evidence of resource acquisition, planning or management. |  |  |  | Resources are being deployed across the organization and individual programmes have an approach to resource acquisition, planning or management. However there is little evidence of consistency of approach. |  |  | The organization has a centrally defined and adopted set of procedures and management processes for acquiring, planning and managing programme resources. |  |  | Resource management for programmes is considered at a strategic level within the organization. There is evidence of resource capacity management, through capacity planning, in order to meet programme delivery needs. |  |  | Resources are deployed optimally. There is clear evidence of load balancing and the effective use of both internal and external resources across all programmes. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: Programmes rarely identify the resources they require or the means to acquire the |  |  | Process: There are a few examples of programmes listing their resource requirements and the means to acquire them in their programme documentation |  |  |  | Process: Our programmes have their own approaches to resource management. Assumptions about resource availability are made |  |  | Process: We have a common approach to resource management that is consistently applied by all programmes, which includes managing the aggregating effect of resources across the programme's projects |  |  | Process: Our common programme resource management process is regularly assessed for past effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our common programme resource management process
| Organization: Acquisition of resources is not managed |  |  | Organization: There are isolated examples of programmes managing the acquisition of their own resources |  |  |  | Organization: Our programmes define responsibilities for managing the acquisition of resources independently of each other |  |  | Organization: Our programmes understand their resource requirements in terms of capacity and capability, and a plan exists to manage them; There is some co-ordination between the Programmes undertaken by a central function. |  |  | Organization: We have a central function that has an aggregated view of resource requirements/ utilization across programmes and our organizational capacity to deliver them |  |  | Organization: We have a central function which ensures we have the capacity to fulfil demand based on forecast resource requirements/utilisation across our programmes
| Performance: Resourcing issues come as a surprise to programmes |  |  | Performance: We are aware of instances of resource conflicts due to the lack of consistency of resource planning |  |  |  | Performance: Resource performance and utilization tracking is taking place in some of our programmes, but it is inconsistently applied |  |  | Performance: Resource performance and utilization tracking is taking place which enables scheduling of key resources between programmes |  |  | Performance: We make adjustments to delivery during the programme lifecycle, to re-balance resource supply and demand. Programmes consistently have sufficient resources to meet their schedule targets. |  |  | Performance: We make pre-emptive interventions based on forecasting performance/utilization to redirect resources in existing programmes (and their constituent projects) in order to optimize the number of programmes/projects we can deliver

## Portefølje
Portfolio Management
P3M3 ® assessment form |  |  | Ja | Nei | Delvis |  | Ja | Nei
Organizational Governance | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This looks at how the delivery of initiatives is aligned to the strategic direction of the organization. It considers how start-up and closure controls are applied to initiatives and how alignment is maintained during an initiative’s life cycle. This differs from management control, which views how control of initiatives is maintained internally, as this perspective looks at how external factors that impact on initiatives are controlled (where possible, or mitigated if not) and used to maximize the final result. Effective sponsorship should enable this. Organizational governance also looks at how a range of other organizational controls are deployed and standards achieved, including legislative and regulatory frameworks. It also considers the levels of analysis of stakeholder engagement and how their requirements are factored into the design and delivery of outputs and outcomes. | The criterias of level 1 are not fullfilled |  |  | The organization has some inconsistent and informal attempts to align individual initiatives to organizational objectives, and there is an ad hoc, inconsistent and ineffective oversight of initiatives. |  |  |  | There are some attempts to recognize the portfolio of initiatives, but there is still little overall leadership and direction for the process. Initiatives may be initiated and run without full regard to the organizational goals, priorities and targets. |  |  | Centrally defined organizational controls are applied consistently to the portfolio(s), with decision-making structures in place and linked to organizational governance. |  |  | All initiatives are integrated into an achievable and governed portfolio which is aligned to strategic objectives and priorities. The portfolio contains relevant information on initiatives (e.g. performance measures, quality attributes and asset management data) to support Executive Board decisions. |  |  | The portfolio is managed to ensure that it remains aligned to support the organization’s strategic objectives. The portfolio management process is optimized to ensure that it is sufficiently dynamic and agile to cater for changes in business direction and priorities. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: Our decisions to approve/amend/stop initiatives are based on the merit of the individual initiative and not in consideration of their place in the wider portfolio. |  |  | Process: Our decision making process to approve/amend/stop initiatives considers their place in the wider portfolio |  |  |  | Process: We have portfolio level processes to translate strategic priorities into initiatives |  |  | Process: We have portfolio level processes in place to regularly review initiatives within the portfolio to check their continued alignment with organizational objectives and priorities. |  |  | Process: We have portfolio level processes to model the impact of change to ensure sustainable business performance |  |  | Process: We have processes in place to regularly review the portfolio to ensure it has the optimal mix of projects and programmes to achieve organizational objectives.
| Organization: Responsibilities for setting portfolio level priorities are not defined |  |  | Organization: There is recognition that defined roles, with responsibilities and accountabilities for portfolio-level decision-making, are required |  |  |  | Organization: A portfolio level decision making body has been established but their terms of reference are still being debated/challenged |  |  | Organization: Roles and Responsibilities for portfolio level decision making bodies are defined and consistently applied across all parts of the organization. |  |  | Organization: Organizational leadership and portfolio leadership are aligned. |  |  | Organization: Our organization structure is optimised to ensure efficiency of decision making whilst ensuring robustness of decisions (i.e. the number of decision-making layers and the authority delegated to them)
| Performance: We don't have a list of initiatives in our portfolio |  |  | Performance: We have a list of the initiatives in our portfolio |  |  |  | Performance: We understand the initiatives in our portfolio and are beginning to identify duplicate and contradictory initiatives |  |  | Performance: Our portfolio is free from duplicate and contradictory initiatives. It is rare for duplicate or contradictory initiatives to be approved. |  |  | Performance: Our portfolio plan includes a pipeline of initiatives in anticipation of forecast performance and organizational priorities. |  |  | Performance: Our portfolio is optimised to maximise the achievement of strategic objectives for the least time, cost and risk.
Management Control | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This covers the internal controls of the initiative and how its direction of travel is maintained throughout its life cycle, with appropriate break points to enable it to be stopped or redirected by a controlling body if necessary. Management control is characterized by clear evidence of leadership and direction, scope, stages, tranches and review processes during the course of the initiative. There will be regular checkpoints and clearly defined decision-making processes. There will be full and clear objectives and descriptions of what the initiative will deliver. Initiatives should have clearly described outputs, a programme may have a blueprint (or target operating model) with defined outcomes, and a portfolio may have an organizational blueprint (or target operating model). Internal structures will be aligned to achieve these characteristics and the focus of control will be on achieving them within the tolerance and boundaries set by the controlling body and based on the broader organizational requirements. Issues will be identified and evaluated, and decisions on how to deal with them will be made using a structured process with appropriate impact assessments. | The criterias of level 1 are not fullfilled |  |  | The organization recognizes the portfolio but has little or nothing in terms of documented processes or standards for managing the portfolio. |  |  |  | There are pockets of portfolio discipline within individual departments, but this is based on key individuals rather than as part of a comprehensive and consistent organization-wide approach. |  |  | Portfolio management processes are centrally defined, documented and understood, as are roles and responsibilities for delivery. |  |  | Portfolio management processes exist and are proven. Portfolio management has established metrics against which the strategic success of the organization can be measured. |  |  | Portfolio management has well-defined controls and behaviours that enable it to deliver the strategic objectives of the organization through a variety of processes and tools. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We have no defined approach to controlling our portfolio, nor are we aware that we may need one |  |  | Process: There is recognition we need portfolio level controls and we are beginning to define them |  |  |  | Process: We have portfolio level prioritization management controls but they are not part of an integrated set of processes |  |  | Process: We have an integrated set of portfolio management processes that interface to project/programme processes as well as the corporate strategic planning processes. |  |  | Process: We review the performance of our portfolio level processes to drive efficiencies and effectiveness (e.g. reducing reporting effort, improving data accuracy, etc.) |  |  | Process: We are able to predict the performance of portfolio controls and use that capability to pro-actively amend processes to ensure they remain optimized
| Organization: Responsibilities for coordinating or tracking the organization's initiatives are not defined |  |  | Organization: We are attempting to establish a portfolio function/office |  |  |  | Organization: We have established a corporate portfolio function/office, but its authority is not fully recognised by the organization |  |  | Organization: The portfolio function/office reports to a member of the senior management team (e.g. board member) |  |  | Organization: The terms of reference for the portfolio function/office are regularly reviewed and updated to ensure it has sufficient authority and accountability to control the portfolio |  |  | Organization: There is clear executive level accountability to ensure portfolios are effectively controlled.
| Performance: We do not understand what initiatives we have running |  |  | Performance: We recognise the need to distinguish change activities from business-as-usual and are beginning to account for them distinctly |  |  |  | Performance: We understand the initiatives in our portfolio and are beginning to identify duplicate and contradictory initiatives |  |  | Performance: We know what key initiatives we are running, their remaining cost, the timing of their expected benefits and the contribution they make as a collective set to our organizational objectives. |  |  | Performance: Initiatives that no longer add value to the portfolio or are deviating from their agreed targets are stopped or amended at the earliest point |  |  | Performance: Senior executives are confident that all strategic objectives can be achieved within target timescale for the optimum total investment
Benefits Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Benefits management is the process that ensures that the desired business change outcomes have been clearly defined are measurable and are ultimately realized through a structured approach and with full organizational ownership. Benefits should be assessed and approved by the organizational areas that will deliver them. Benefit dependencies and other requirements are clearly defined and understanding gained on how the outputs of the initiative will meet those requirements. There should be evidence of suitable classification of benefits and a holistic view of the implications being considered. All benefits should be owned, have realization plans and be actively managed to ensure that they are achieved. There will be a focus on operational transition, coupled with follow-up activities to ensure that benefits are being owned and realized by the organization. There will be evidence of continual improvement being embedded in the way the organization functions. This process will identify opportunities that can be delivered by initiatives and also take ownership of the exploitation of capabilities delivered by programmes and projects. Change management, and the complexities this brings, will also be built into the organization’s approach. | The criterias of level 1 are not fullfilled |  |  | There is some recognition that initiatives may exist within the organizational and divisional portfolio to enable the achievement of benefits for the organization. However, there is no defined benefits realization process. |  |  |  | The development of the investment cycle will increase the awareness of the importance of identifying benefits and subsequently tracking whether they have been realized. However, the realization of benefits is still likely to be patchy, inconsistent and unmonitored. |  |  | There is a centrally managed framework used for defining and tracking the realization of portfolio-level benefits across the business operations |  |  | The benefits realization and management process is well established, measurable and is integrated into how the organization manages itself. |  |  | Benefits realization is integral to the development of business strategy decision-making. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognize benefits management activities as part of a portfolio management process |  |  | Process: We have processes in place to collate benefits from individual initiatives |  |  |  | Process: We have agreed rules to define how benefits should be categorized, quantified, valued and validated |  |  | Process: The portfolio understands the benefits the organization can realize from the successful delivery of its constituent programmes and projects |  |  | Process: Our portfolio benefits management processes are regularly assessed for effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our portfolio benefit management process
| Organization: Responsibilities for ensuring the realisation of benefits are realised are not defined |  |  | Organization: Operational managers are occasionally identified to manage benefits realization |  |  |  | Organization: There are accountabilities for individuals or control groups to take action to review benefits and benefits realization plans |  |  | Organization: There are close working relationships between the portfolio office and the organizational investment committee |  |  | Organization: We have a portfolio office with responsibilities to maximise the contribution to operational performance and strategic objectives |  |  | Organization: Our organizational structure includes responsibility for maximising return from portfolio investments within the operational environment
| Performance: We neither define nor measure portfolio benefits |  |  | Performance: Our portfolio realizes few of its expected benefits |  |  |  | Performance: Our portfolio delivers some its expected benefits, but evidence can be anecdotal |  |  | Performance: Our portfolio delivers most of its defined benefits, but evidence may not always be available |  |  | Performance: Our portfolio delivers nearly all of its expected benefits, and this can be evidenced |  |  | Performance: Benefits are reviewed throughout the business change lifecycle taking into account the needs of the operational environment and not solely to justify an investment
Risk Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
This views the way in which the organization manages threats to, and opportunities presented by, the initiative. Risk management maintains a balance of focus on threats and opportunities, with appropriate management actions to minimize or eliminate the likelihood of any identified threat occurring, or to minimize its impact if it does occur, and maximize opportunities. It will look at a variety of risk types, both internal and external, that affect the initiative and will focus on tracking the triggers that create risks. Responses to risk will be innovative and proactive, using a number of options to minimize threats and maximise opportunities. The review of risk will be embedded within the initiative’s life cycle and have a supporting process and structures to ensure that the appropriate levels of rigour are being applied, with evidence of interventions and changes made to manage risks. | The criterias of level 1 are not fullfilled |  |  | There is a growing recognition that risks need to be managed and that, at least for key business initiatives (e.g. cost saving or major site developments), they can threaten success. There may be evidence of risks being documented but little evidence of active management. |  |  |  | There is generally a top-down approach to risk identification, focusing on major organizational initiatives, but some initiatives are increasingly carrying out bottom-up risk identification. However, these approaches are inconsistent, not particularly interrelated and often do not address the actual management of risks. |  |  | Portfolio risks are identified and quantified, and response plans are developed and funded. Risk management across the portfolio(s) is based on a common, centrally managed process. |  |  | The organization’s appetite for risk, and the balance of threats and opportunities across the portfolio, are continually reviewed and managed. Senior management own and oversee risk management across the portfolio. |  |  | Risk management is embedded in the culture of the organization and underpins all decision-making with the portfolio(s). There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise risk management activities as part of our portfolio management processes |  |  | Process: Our portfolios do not differentiate portfolio level risks from programme/project level risks |  |  |  | Process: Our processes require us to differentiate portfolio level risks from programme/project risks, but this does not occur consistently |  |  | Process: The portfolio demonstrated in reporting that it understands the risks to the organization from its constituent programmes, projects and operations |  |  | Process: Our portfolio risk management process is regularly assessed for effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our portfolio risk management process
| Organization: Responsibilities for managing risks to the portfolio are not defined |  |  | Organization: Risk owners understand and manage risk, but without consistent processes, some risks are managed sub-optimally; it is hard to aggregate risk |  |  |  | Organization: There are accountabilities for individuals or control groups to take action to reduce the impact of portfolio level risks |  |  | Organization: There are close working relationships between the portfolio office and the organizational risk function (or equivalent) |  |  | Organization: We have a portfolio office with responsibilities to balance the risk profile of the portfolio (e.g. high-risk/high-return and low-risk/low-return initiatives) |  |  | Organization: Our organizational structure includes responsibility for pre-emptive interventions to re-direct existing programmes/ projects based on threats and opportunities
| Performance: We are unaware of what type of dependencies exist within the portfolio |  |  | Performance: The portfolio underperforms as a result of risks that could have been anticipated |  |  |  | Performance: Our portfolio mainly anticipates its risks, but some areas underperform as a result of risks that could have been anticipated |  |  | Performance: We understand and track the return from our investment in risk management |  |  | Performance: Our portfolio is generally able to handle events that were unpredictable (unknown unknowns) through budgetary contingency and early warning mechanisms |  |  | Performance: We are able to optimise our portfolio through understanding its risk profiles
Stakeholder Engagement | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Stakeholders are key to the success of any initiative. Stakeholders at different levels, both within and outside the organization, will need to be analyzed and engaged with effectively in order to achieve objectives in terms of support and engagement. Stakeholder engagement includes communications planning, the effective identification and use of different communications channels, and techniques to enable objectives to be achieved. Stakeholder engagement should be seen as an ongoing process across all initiatives and one that is inherently linked to the initiative’s life cycle and governance controls. | The criterias of level 1 are not fullfilled |  |  | Stakeholder engagement and communication is rarely used by portfolios as an element of the delivery toolkit. |  |  |  | Portfolios will be communicated to stakeholders, but this is linked more to the personal initiative of portfolio managers than to a structured approach deployed by the organization. |  |  | There is a centrally managed and consistent approach to stakeholder engagement and communications used on the portfolio(s). |  |  | Sophisticated techniques are used to analyze and engage the portfolio stakeholder environment effectively, and quantitative information is used to underpin the assessment of effectiveness. |  |  | Communications are being optimized from extensive knowledge of the stakeholder environment, to enable the portfolio(s) to achieve their objectives. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognize stakeholder management activities as part of our portfolio management process |  |  | Process: Processes to identify key stakeholders relating to the portfolio are in place |  |  |  | Process: The portfolio uses some form of stakeholder management framework for identifying stakeholders and stakeholder groups |  |  | Process: We have a documented and published stakeholder management policy, strategy and process for the portfolio to follow, and it is being followed. |  |  | Process: Our portfolio stakeholder management process is regularly assessed for effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our portfolio stakeholder management process
| Organization: Responsibilities for ensuring that our portfolio communications is managed are not defined |  |  | Organization: Some roles and responsibilities for portfolio stakeholder management and communications are defined, but others are not. |  |  |  | Organization: Individuals or groups have defined responsibilities for communicating on behalf of the portfolio, but these are not consistent across the organization |  |  | Organization: The relationship and responsibilities between the portfolio people responsible for stakeholder management and the people responsible for corporate communications are centrally defined |  |  | Organization: We consolidate opportunities to communicate to enable more efficient delivery of messages |  |  | Organization: Our organization structure includes responsibility for ensuring that the needs of the portfolio's customers (both internal and external) are met
| Performance: Stakeholders are generally unaware of the portfolio's status |  |  | Performance: Our portfolio roles communicate independently of each other |  |  |  | Performance: We are aware of instances of stakeholders receiving multiple or conflicting messages from different sources due to the lack of co-ordination |  |  | Performance: We check for the success of communications and there are techniques for handling feedback |  |  | Performance: We have an on-going review of communications effectiveness with improvements being made |  |  | Performance: Stakeholder reactions are analyzed, and evidence of proactive communications management to influence stakeholder attitudes and levels of support is maintained
Financial Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Finance is an essential resource that should be a key focus for initiating and controlling initiatives. Financial management ensures that the likely costs of the initiative are captured and evaluated within a formal business case and that costs are categorized and managed over the investment life cycle. There should be evidence of the appropriate involvement of the organization’s financial functions, with approvals being embedded in the broader organizational hierarchy. The business case, or equivalent, should define the value of the initiative to the business and contain a financial appraisal of the possible options. The business case will be at the core of decision-making during the initiative’s life cycle, and may be linked to formal review stages and evaluation of the cost and benefits associated with alternative actions. Financial management will schedule the availability of funds to support the investment decisions. | The criterias of level 1 are not fullfilled |  |  | There is some recognition that initiatives may exist within the organizational and divisional portfolio to enable the Portfolio oversight of the financial aspects of initiatives may be recognized but there is little or no organizational investment control. |  |  |  | There are business cases being produced and some, usually departmental, structures to oversee investment decisions. However, business cases are often appraised independently of each other and real organizational priorities have not been established. |  |  | There are established standards for the investment management process and the preparation of business cases. Portfolio investment costs are monitored and controlled. |  |  | The organization has effective and robust financial control of its investment decisions and the approval and monitoring of initiatives. There is proactive, evidence-based management of the portfolio investment funds and costs. |  |  | Financial control of the portfolio is an integral part of the organization’s financial control regime. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise finance management activities are part of our portfolio management process |  |  | Process: We are starting to aggregate financial information from all of the initiatives in our portfolio |  |  |  | Process: We have agreed rules about how to compile cost forecasts (e.g. such as capital and operating expenditure) and for valuing efficiency savings and other benefits in our business cases |  |  | Process: We have centrally agreed portfolio investment management process and practices in place which are used across the organization |  |  | Process: Our portfolio finance management process is regularly assessed for effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our finance management process
| Organization: Responsibilities for ensuring that our financial analysis of the portfolio is undertaken are not defined |  |  | Organization: Finance managers are occasionally identified to manage the portfolio finances |  |  |  | Organization: There are formal commitments from individuals or control groups to take action to review spend against the portfolio-level financial plan |  |  | Organization: We have a portfolio office with responsibilities to align portfolio finances with the organization's financial management processes |  |  | Organization: Our portfolio office regularly reviews the performance of portfolio level financial processes |  |  | Organization: Our organizational structure includes responsibility for reallocating emerging underspends to fund new initiatives from the development pipeline
| Performance: We do not know the forecasted spend profile for our portfolio |  |  | Performance: We understand the forecasted spend profile for parts of our portfolio |  |  |  | Performance: We understand the forecasted spend profile for most of our portfolio |  |  | Performance: We understand the forecasted spend profile for our entire portfolio with a high degree of confidence |  |  | Performance: Our portfolio delivers within its forecasted spend profile |  |  | Performance: We are able to flex our appetite for financial risk to better align the portfolio to meet organizational objectives
Resource Management | No maturity level achieved | Findings / Comments |  | Level 1 | Findings / Comments | Assess-ment |  | Level 2 | Findings / Comments | Assess-ment | Level 3 | Findings / Comments | Assess-ment | Level 4 | Findings / Comments | Assess-ment | Level 5 | Findings / Comments | Assess-ment
Resource management covers management of all types of resources required for delivery. These include human resources, buildings, equipment, supplies, information, tools and supporting teams. A key element of resource management is the process for acquiring resources and how supply chains are utilized to maximize effective use of resources. There will be evidence of capacity planning and prioritization to enable effective resource management. This will also include performance management and exploitation of opportunities for greater utilization. Resource capacity considerations will be extended to the capacity of the operational groups to resource the implications of change. | The criterias of level 1 are not fullfilled |  |  | Portfolio resource requirements are recognized but not systematically managed. Resource allocation is ad hoc, with little, if any, profiling of resources to meet the resource requirements of specific initiatives. |  |  |  | The organization has started to develop portfolio resource management processes and improve the identification and allocation of resources to specific initiatives. However, this is likely to be reliant on key individuals and does not assess the impact of resource allocation against the strategic objectives and priorities. |  |  | The portfolio resource management process is centrally defined within the organization. Initiative resource needs are evaluated, enabling the organization to target and increase the development of resources to meet strategic objectives and priorities. |  |  | The organization has established effective capacity and capability strategies and processes for obtaining, allocating and adjusting resource levels (including people, funding, estate and tools) in line with medium- and long-term investment plans. |  |  | Portfolio management drives the planning, development and allocation of initiatives to optimize the effective use of resources in achieving the strategic objectives and priorities. There is an organization-wide resource management policy and strategy for the use of internal and external resources. There is evidence of continual improvement.
| Attributes | Findings / Comments |  | Attributes | Findings / Comments | Asess-ment |  | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment | Attributes | Findings / Comments | Asess-ment
| Process: We do not recognise resource management activities as part of our portfolio management processes |  |  | Process: We are starting to collate resource requirements from individual initiatives |  |  |  | Process: We categorise resources (e.g. people, equipment, etc.) |  |  | Process: We aggregate the resource demands from initiatives and have a resource demand plan along with a capability development plan for the people it requires |  |  | Process: Our portfolio resource management process is regularly assessed for effectiveness and refined when appropriate |  |  | Process: We are continually monitoring for opportunities to improve the effectiveness of our portfolio resource management process
| Organization: Responsibility for acquiring and allocating resources is not defined |  |  | Organization: Responsibility for acquiring and allocating resources is defined for parts of the portfolio |  |  |  | Organization: There are accountabilities for individuals or control groups to take action to assess portfolio resource requirements |  |  | Organization: We have a central function that has an aggregated view of resource requirements across initiatives and the organization's capacity |  |  | Organization: Portfolio resource management is embedded within organizational reporting, governance and management structures |  |  | Organization: Our organizational structure includes responsibility for ensuring that capacity can fulfil demand based on forecast resource requirements across the portfolio
| Performance: We don't check to see if the right resources are available when we need them |  |  | Performance: We are aware of instances of resource conflicts due to the lack of consistency of resource planning |  |  |  | Performance: Tracking of resource utilization and development is taking place in some parts of the portfolio but it is inconsistently applied |  |  | Performance: Resource performance tracking and utilization is in place in all parts of the portfolio which enables scheduling and movement of key resources between initiates |  |  | Performance: Our portfolio matches resource supply and demand, and arranges to acquire additional resource as needed |  |  | Performance: We make adjustments to balance/re-prioritize the portfolio taking into account available resources